## Sheet1
Project Planner
Task Name | Description | Start Date | End Date | Duration | Project Completion
Phase 1
Task 1 | Project Initiation | 2023-10-02 | 2024-01-20 | 3 | 100%
Task 2 | Site Selection and Acquisition | 2024-02-10 | 2024-03-20 | 1 | 100%
Task 3 | Environmental Impact Assessment | 2024-04-23 | 2024-05-04 | 1 | 100%
Task 4 | Design Development | 2024-05-14 | 2024-07-18 | 2 | 100%
Task 5 | Community Engagement | 2024-08-19 | 2024-08-25 | 0 | 99%
Task 6 | Budgeting and Funding | 2024-08-30 | 2024-09-02 | 1 | 98%
Task 7 | Groundwork and Site Preparation | 2024-10-15 | 2024-10-25 | 0 | 100%
Task 8 | Sustainable Landscaping | 2024-11-01 | 2024-11-30 | 1 | 100%
Task 9 | Irrigation and Water Management | 2024-12-10 | 2024-12-31 | 1 | 100%
Task 10 | Planting Trees and Vegetation | 2025-01-08 | 2025-02-10 | 1 | 100%
Task 11 | Installation of Park Amenities | 2025-02-25 | 2025-03-10 | 1 | 100%
Task 12 | Maintenance and Upkeep Planning | 2025-03-15 | 2025-05-20 | 2 | 100%
Task 13 | Project Closure and Handover | 2025-06-10 | 2025-08-25 | 2 | 100%